## Implementation Tracker
Clause | Sub-Clause | Sub-Clause Title | Task # | Task Description | Responsible | Owner (Name) | Target Date | Status | % Complete | Evidence Required | Regulatory Alignment | Evidence Location | Notes
4 | 4.1 | Understanding the Organization and Its Context | 1 | Identify internal factors: AI capabilities, legacy systems, data infrastructure, risk culture, governance maturity | CRO, AI Governance Lead, Head of Technology |  |  | Not Started | 0% | Organizational context report, PESTLE analysis, AI maturity assessment, AI-to-business mapping | APRA CPS 230
4 | 4.1 | Understanding the Organization and Its Context | 2 | Identify external factors: financial regulations (APRA CPS 230/234, Basel, MiFID II, DORA, EU AI Act), market conditions | CRO, AI Governance Lead, Head of Technology |  |  | Not Started | 0% | Organizational context report, PESTLE analysis, AI maturity assessment, AI-to-business mapping | APRA CPS 230
4 | 4.1 | Understanding the Organization and Its Context | 3 | Document AI-specific context: AI maturity level, strategic AI roadmap, competitive positioning | CRO, AI Governance Lead, Head of Technology |  |  | Not Started | 0% | Organizational context report, PESTLE analysis, AI maturity assessment, AI-to-business mapping | APRA CPS 230
4 | 4.1 | Understanding the Organization and Its Context | 4 | Conduct PESTLE analysis with financial-services-specific AI considerations | CRO, AI Governance Lead, Head of Technology |  |  | Not Started | 0% | Organizational context report, PESTLE analysis, AI maturity assessment, AI-to-business mapping | APRA CPS 230
4 | 4.1 | Understanding the Organization and Its Context | 5 | Map AI systems to financial services functions: credit scoring, fraud detection, AML/KYC, trading, claims, onboarding, robo-advisory | CRO, AI Governance Lead, Head of Technology |  |  | Not Started | 0% | Organizational context report, PESTLE analysis, AI maturity assessment, AI-to-business mapping | APRA CPS 230
4 | 4.1 | Understanding the Organization and Its Context | 6 | Assess interaction between AI governance and existing financial risk frameworks (operational risk, model risk, conduct risk) | CRO, AI Governance Lead, Head of Technology |  |  | Not Started | 0% | Organizational context report, PESTLE analysis, AI maturity assessment, AI-to-business mapping | APRA CPS 230
4 | 4.2 | Needs and Expectations of Interested Parties | 1 | Identify interested parties: customers, regulators (APRA, ASIC, FCA, ECB, SEC), shareholders, auditors, data subjects | AI Governance Lead, Legal/Compliance, Regulatory Affairs |  |  | Not Started | 0% | Interested parties register, regulatory requirements matrix, stakeholder mapping, horizon scanning log | Multiple (APRA, Basel, EU AI Act)
4 | 4.2 | Needs and Expectations of Interested Parties | 2 | Document regulatory expectations: SR 11-7, APRA CPG 235, CPS 234, EU AI Act risk tiers | AI Governance Lead, Legal/Compliance, Regulatory Affairs |  |  | Not Started | 0% | Interested parties register, regulatory requirements matrix, stakeholder mapping, horizon scanning log | Multiple (APRA, Basel, EU AI Act)
4 | 4.2 | Needs and Expectations of Interested Parties | 3 | Map stakeholder concerns to AI systems (e.g., customer fairness in credit decisions, explainability) | AI Governance Lead, Legal/Compliance, Regulatory Affairs |  |  | Not Started | 0% | Interested parties register, regulatory requirements matrix, stakeholder mapping, horizon scanning log | Multiple (APRA, Basel, EU AI Act)
4 | 4.2 | Needs and Expectations of Interested Parties | 4 | Document requirements from financial industry bodies (OECD AI Principles, FSB recommendations) | AI Governance Lead, Legal/Compliance, Regulatory Affairs |  |  | Not Started | 0% | Interested parties register, regulatory requirements matrix, stakeholder mapping, horizon scanning log | Multiple (APRA, Basel, EU AI Act)
4 | 4.2 | Needs and Expectations of Interested Parties | 5 | Assess third-party expectations from banking partners, payment networks, outsourcing providers | AI Governance Lead, Legal/Compliance, Regulatory Affairs |  |  | Not Started | 0% | Interested parties register, regulatory requirements matrix, stakeholder mapping, horizon scanning log | Multiple (APRA, Basel, EU AI Act)
4 | 4.2 | Needs and Expectations of Interested Parties | 6 | Establish ongoing regulatory horizon scanning and stakeholder engagement process | AI Governance Lead, Legal/Compliance, Regulatory Affairs |  |  | Not Started | 0% | Interested parties register, regulatory requirements matrix, stakeholder mapping, horizon scanning log | Multiple (APRA, Basel, EU AI Act)
4 | 4.3 | Determining the Scope of the AIMS | 1 | Define AIMS boundaries across business lines (retail, corporate, wealth, insurance, trading, payments) | CRO, AI Governance Lead, Head of Compliance |  |  | Not Started | 0% | AIMS scope statement, AI system inventory with risk classification, MRM alignment | APRA CPS 230, EU AI Act
4 | 4.3 | Determining the Scope of the AIMS | 2 | Identify all AI systems in scope: models, ML pipelines, third-party AI, LLM-based tools | CRO, AI Governance Lead, Head of Compliance |  |  | Not Started | 0% | AIMS scope statement, AI system inventory with risk classification, MRM alignment | APRA CPS 230, EU AI Act
4 | 4.3 | Determining the Scope of the AIMS | 3 | Classify AI systems by EU AI Act risk tier where applicable | CRO, AI Governance Lead, Head of Compliance |  |  | Not Started | 0% | AIMS scope statement, AI system inventory with risk classification, MRM alignment | APRA CPS 230, EU AI Act
4 | 4.3 | Determining the Scope of the AIMS | 4 | Document exclusions with risk-based justification | CRO, AI Governance Lead, Head of Compliance |  |  | Not Started | 0% | AIMS scope statement, AI system inventory with risk classification, MRM alignment | APRA CPS 230, EU AI Act
4 | 4.3 | Determining the Scope of the AIMS | 5 | Consider AI lifecycle across regulated activities | CRO, AI Governance Lead, Head of Compliance |  |  | Not Started | 0% | AIMS scope statement, AI system inventory with risk classification, MRM alignment | APRA CPS 230, EU AI Act
4 | 4.3 | Determining the Scope of the AIMS | 6 | Publish scope statement aligned with MRM framework | CRO, AI Governance Lead, Head of Compliance |  |  | Not Started | 0% | AIMS scope statement, AI system inventory with risk classification, MRM alignment | APRA CPS 230, EU AI Act
4 | 4.4 | AI Management System | 1 | Establish AIMS integrated with MRM, Operational Risk, IT Risk, Data Governance | AI Governance Lead, CRO, CTO |  |  | Not Started | 0% | AIMS process map, Three Lines of Defence matrix, governance committee charter | SR 11-7, APRA
4 | 4.4 | AI Management System | 2 | Document process maps showing Three Lines of Defence integration | AI Governance Lead, CRO, CTO |  |  | Not Started | 0% | AIMS process map, Three Lines of Defence matrix, governance committee charter | SR 11-7, APRA
4 | 4.4 | AI Management System | 3 | Define alignment with ISO 27001, ISO 31000, SOC 2 | AI Governance Lead, CRO, CTO |  |  | Not Started | 0% | AIMS process map, Three Lines of Defence matrix, governance committee charter | SR 11-7, APRA
4 | 4.4 | AI Management System | 4 | Establish AI governance committee with Risk, Compliance, Technology, Business, and Data representation | AI Governance Lead, CRO, CTO |  |  | Not Started | 0% | AIMS process map, Three Lines of Defence matrix, governance committee charter | SR 11-7, APRA
5 | 5.1 | Leadership and Commitment | 1 | Board/ExCo formally endorses AIMS and responsible AI strategy | Board, CEO, CRO, CTO |  |  | Not Started | 0% | Board resolution/minutes, AI strategy, resource allocation records, committee reporting packs | APRA CPS 220, SR 11-7
5 | 5.1 | Leadership and Commitment | 2 | Align AI strategy with risk appetite framework and strategic plan | Board, CEO, CRO, CTO |  |  | Not Started | 0% | Board resolution/minutes, AI strategy, resource allocation records, committee reporting packs | APRA CPS 220, SR 11-7
5 | 5.1 | Leadership and Commitment | 3 | Allocate resources: AI governance team, model validation unit, compliance support, technology budget | Board, CEO, CRO, CTO |  |  | Not Started | 0% | Board resolution/minutes, AI strategy, resource allocation records, committee reporting packs | APRA CPS 220, SR 11-7
5 | 5.1 | Leadership and Commitment | 4 | Communicate responsible AI expectations across all business lines | Board, CEO, CRO, CTO |  |  | Not Started | 0% | Board resolution/minutes, AI strategy, resource allocation records, committee reporting packs | APRA CPS 220, SR 11-7
5 | 5.1 | Leadership and Commitment | 5 | Integrate AI governance into Board risk committee and audit committee reporting | Board, CEO, CRO, CTO |  |  | Not Started | 0% | Board resolution/minutes, AI strategy, resource allocation records, committee reporting packs | APRA CPS 220, SR 11-7
5 | 5.1 | Leadership and Commitment | 6 | Ensure senior management accountability for AI outcomes per regulatory expectations | Board, CEO, CRO, CTO |  |  | Not Started | 0% | Board resolution/minutes, AI strategy, resource allocation records, committee reporting packs | APRA CPS 220, SR 11-7
5 | 5.2 | AI Policy | 1 | Develop AI policy: responsible AI, regulatory compliance, model risk, data ethics, customer fairness | CRO, AI Governance Lead, Legal, Compliance |  |  | Not Started | 0% | AI Policy (board-approved), alignment matrix, GenAI acceptable use policy, comms records | SR 11-7, APRA, FCA, EU AI Act
5 | 5.2 | AI Policy | 2 | Include: explainability in customer-facing decisions, non-discrimination, human oversight of high-risk AI | CRO, AI Governance Lead, Legal, Compliance |  |  | Not Started | 0% | AI Policy (board-approved), alignment matrix, GenAI acceptable use policy, comms records | SR 11-7, APRA, FCA, EU AI Act
5 | 5.2 | AI Policy | 3 | Address: fair lending, market integrity, consumer protection, financial inclusion | CRO, AI Governance Lead, Legal, Compliance |  |  | Not Started | 0% | AI Policy (board-approved), alignment matrix, GenAI acceptable use policy, comms records | SR 11-7, APRA, FCA, EU AI Act
5 | 5.2 | AI Policy | 4 | Align with Model Risk Policy, Data Governance Policy, Code of Conduct, Privacy Policy | CRO, AI Governance Lead, Legal, Compliance |  |  | Not Started | 0% | AI Policy (board-approved), alignment matrix, GenAI acceptable use policy, comms records | SR 11-7, APRA, FCA, EU AI Act
5 | 5.2 | AI Policy | 5 | Address generative AI / LLM use by staff (acceptable use, data leakage prevention) | CRO, AI Governance Lead, Legal, Compliance |  |  | Not Started | 0% | AI Policy (board-approved), alignment matrix, GenAI acceptable use policy, comms records | SR 11-7, APRA, FCA, EU AI Act
5 | 5.2 | AI Policy | 6 | Approve, communicate, schedule periodic reviews (min. annually or on regulatory change) | CRO, AI Governance Lead, Legal, Compliance |  |  | Not Started | 0% | AI Policy (board-approved), alignment matrix, GenAI acceptable use policy, comms records | SR 11-7, APRA, FCA, EU AI Act
5 | 5.3 | Roles, Responsibilities and Authorities | 1 | Define roles aligned to Three Lines of Defence: 1L (business), 2L (risk/validation), 3L (audit) | CRO, HR, Board Risk Committee |  |  | Not Started | 0% | RACI matrix, AI governance org chart, committee charter, role descriptions, escalation procedure | SR 11-7, Three Lines
5 | 5.3 | Roles, Responsibilities and Authorities | 2 | Assign: AI Governance Lead, Chief Model Risk Officer, AI Ethics Lead, DPO, Model Validation Head | CRO, HR, Board Risk Committee |  |  | Not Started | 0% | RACI matrix, AI governance org chart, committee charter, role descriptions, escalation procedure | SR 11-7, Three Lines
5 | 5.3 | Roles, Responsibilities and Authorities | 3 | Establish AI Risk Committee with clear mandate and authority | CRO, HR, Board Risk Committee |  |  | Not Started | 0% | RACI matrix, AI governance org chart, committee charter, role descriptions, escalation procedure | SR 11-7, Three Lines
5 | 5.3 | Roles, Responsibilities and Authorities | 4 | Document RACI for model development, validation, deployment approval, ongoing monitoring | CRO, HR, Board Risk Committee |  |  | Not Started | 0% | RACI matrix, AI governance org chart, committee charter, role descriptions, escalation procedure | SR 11-7, Three Lines
5 | 5.3 | Roles, Responsibilities and Authorities | 5 | Ensure segregation of duties between model development (1L) and validation (2L) | CRO, HR, Board Risk Committee |  |  | Not Started | 0% | RACI matrix, AI governance org chart, committee charter, role descriptions, escalation procedure | SR 11-7, Three Lines
5 | 5.3 | Roles, Responsibilities and Authorities | 6 | Define escalation paths to CRO/Board for high-risk AI decisions and material model failures | CRO, HR, Board Risk Committee |  |  | Not Started | 0% | RACI matrix, AI governance org chart, committee charter, role descriptions, escalation procedure | SR 11-7, Three Lines
6 | 6.1 | Actions to Address Risks and Opportunities | 1 | Conduct AI risk assessment aligned with operational risk framework and model risk taxonomy | CRO, AI Governance Lead, Model Risk, Operational Risk |  |  | Not Started | 0% | AI Risk Assessment, integrated risk register, risk appetite alignment, treatment plans, concentration risk analysis | CPS 220, Basel, SR 11-7
6 | 6.1 | Actions to Address Risks and Opportunities | 2 | Identify FS-specific risks: algorithmic bias in lending, model drift, adversarial attacks, data poisoning, over-reliance on AI | CRO, AI Governance Lead, Model Risk, Operational Risk |  |  | Not Started | 0% | AI Risk Assessment, integrated risk register, risk appetite alignment, treatment plans, concentration risk analysis | CPS 220, Basel, SR 11-7
6 | 6.1 | Actions to Address Risks and Opportunities | 3 | Assess concentration risk from third-party AI/ML platforms | CRO, AI Governance Lead, Model Risk, Operational Risk |  |  | Not Started | 0% | AI Risk Assessment, integrated risk register, risk appetite alignment, treatment plans, concentration risk analysis | CPS 220, Basel, SR 11-7
6 | 6.1 | Actions to Address Risks and Opportunities | 4 | Assess conduct risk: AI-driven mis-selling, unfair pricing, market manipulation, suitability failures | CRO, AI Governance Lead, Model Risk, Operational Risk |  |  | Not Started | 0% | AI Risk Assessment, integrated risk register, risk appetite alignment, treatment plans, concentration risk analysis | CPS 220, Basel, SR 11-7
6 | 6.1 | Actions to Address Risks and Opportunities | 5 | Map AI risks to risk appetite statements; define AI-specific tolerance thresholds | CRO, AI Governance Lead, Model Risk, Operational Risk |  |  | Not Started | 0% | AI Risk Assessment, integrated risk register, risk appetite alignment, treatment plans, concentration risk analysis | CPS 220, Basel, SR 11-7
6 | 6.1 | Actions to Address Risks and Opportunities | 6 | Define treatment plans aligned to APRA CPS 220 / Basel BCBS 239 | CRO, AI Governance Lead, Model Risk, Operational Risk |  |  | Not Started | 0% | AI Risk Assessment, integrated risk register, risk appetite alignment, treatment plans, concentration risk analysis | CPS 220, Basel, SR 11-7
6 | 6.1 | Actions to Address Risks and Opportunities | 7 | Establish AI risk register integrated with enterprise risk register | CRO, AI Governance Lead, Model Risk, Operational Risk |  |  | Not Started | 0% | AI Risk Assessment, integrated risk register, risk appetite alignment, treatment plans, concentration risk analysis | CPS 220, Basel, SR 11-7
6 | 6.1.4 | AI System Impact Assessment | 1 | Develop methodology covering: customers, financial stability, market integrity, vulnerable populations | AI Governance Lead, Model Risk, Ethics Committee, Compliance |  |  | Not Started | 0% | Impact assessment template (FS-specific), completed assessments, disparate impact analyses, PIAs | EU AI Act, Fair Lending, APPs
6 | 6.1.4 | AI System Impact Assessment | 2 | Conduct impact assessments with focus on fair lending, disparate impact, accessibility | AI Governance Lead, Model Risk, Ethics Committee, Compliance |  |  | Not Started | 0% | Impact assessment template (FS-specific), completed assessments, disparate impact analyses, PIAs | EU AI Act, Fair Lending, APPs
6 | 6.1.4 | AI System Impact Assessment | 3 | Assess impacts on financially vulnerable customers and potential for financial exclusion | AI Governance Lead, Model Risk, Ethics Committee, Compliance |  |  | Not Started | 0% | Impact assessment template (FS-specific), completed assessments, disparate impact analyses, PIAs | EU AI Act, Fair Lending, APPs
6 | 6.1.4 | AI System Impact Assessment | 4 | Evaluate systemic risk implications (correlated AI trading strategies, procyclical credit models) | AI Governance Lead, Model Risk, Ethics Committee, Compliance |  |  | Not Started | 0% | Impact assessment template (FS-specific), completed assessments, disparate impact analyses, PIAs | EU AI Act, Fair Lending, APPs
6 | 6.1.4 | AI System Impact Assessment | 5 | Assess privacy impact aligned with APPs / GDPR (credit data, transaction data, biometric data) | AI Governance Lead, Model Risk, Ethics Committee, Compliance |  |  | Not Started | 0% | Impact assessment template (FS-specific), completed assessments, disparate impact analyses, PIAs | EU AI Act, Fair Lending, APPs
6 | 6.1.4 | AI System Impact Assessment | 6 | Document results with links to control requirements and remediation actions | AI Governance Lead, Model Risk, Ethics Committee, Compliance |  |  | Not Started | 0% | Impact assessment template (FS-specific), completed assessments, disparate impact analyses, PIAs | EU AI Act, Fair Lending, APPs
6 | 6.2 | AI Objectives and Planning | 1 | Establish measurable objectives: accuracy, fairness metrics, explainability coverage, time-to-validation | CRO, AI Governance Lead, Business Line Heads |  |  | Not Started | 0% | AI Objectives, KRI/KPI dashboard, Board reporting pack, review records
6 | 6.2 | AI Objectives and Planning | 2 | Define compliance objectives: 100% high-risk AI validated pre-deployment, regulator SLAs met | CRO, AI Governance Lead, Business Line Heads |  |  | Not Started | 0% | AI Objectives, KRI/KPI dashboard, Board reporting pack, review records
6 | 6.2 | AI Objectives and Planning | 3 | Set customer outcome objectives: reduced unfair denials, improved transparency | CRO, AI Governance Lead, Business Line Heads |  |  | Not Started | 0% | AI Objectives, KRI/KPI dashboard, Board reporting pack, review records
6 | 6.2 | AI Objectives and Planning | 4 | Define actions, resources, responsible person, timeline, KPIs for each objective | CRO, AI Governance Lead, Business Line Heads |  |  | Not Started | 0% | AI Objectives, KRI/KPI dashboard, Board reporting pack, review records
6 | 6.2 | AI Objectives and Planning | 5 | Align AI objectives with institutional KRIs; report to Board Risk Committee | CRO, AI Governance Lead, Business Line Heads |  |  | Not Started | 0% | AI Objectives, KRI/KPI dashboard, Board reporting pack, review records
6 | 6.3 | Planning of Changes | 1 | Establish change management aligned with IT change and model change procedures | AI Governance Lead, Change Management, Model Risk |  |  | Not Started | 0% | Change procedure, materiality matrix, change log, PIR records
6 | 6.3 | Planning of Changes | 2 | Define materiality thresholds for changes requiring re-validation or re-approval | AI Governance Lead, Change Management, Model Risk |  |  | Not Started | 0% | Change procedure, materiality matrix, change log, PIR records
6 | 6.3 | Planning of Changes | 3 | Assess regulatory impact of AIMS changes (e.g., new AI use case requiring notification) | AI Governance Lead, Change Management, Model Risk |  |  | Not Started | 0% | Change procedure, materiality matrix, change log, PIR records
6 | 6.3 | Planning of Changes | 4 | Document change requests, risk assessments, approvals, post-implementation reviews | AI Governance Lead, Change Management, Model Risk |  |  | Not Started | 0% | Change procedure, materiality matrix, change log, PIR records
7 | 7.1 | Resources | 1 | Determine resources: AI governance team, model validation, data scientists, compliance, AI audit capability | CFO, CRO, HR, CTO |  |  | Not Started | 0% | Resource plan, budget allocation, capability gap analysis, headcount plans
7 | 7.1 | Resources | 2 | Assess capability gaps in MRM, AI ethics, explainability, fairness testing | CFO, CRO, HR, CTO |  |  | Not Started | 0% | Resource plan, budget allocation, capability gap analysis, headcount plans
7 | 7.1 | Resources | 3 | Budget for: governance tools, independent validation, external expertise, regulatory engagement | CFO, CRO, HR, CTO |  |  | Not Started | 0% | Resource plan, budget allocation, capability gap analysis, headcount plans
7 | 7.1 | Resources | 4 | Ensure adequate 2L validation resources independent of 1L development | CFO, CRO, HR, CTO |  |  | Not Started | 0% | Resource plan, budget allocation, capability gap analysis, headcount plans
7 | 7.2 | Competence | 1 | Define competencies: model developers (ML + domain), validators (stats + regulation), AI auditors | HR, AI Governance Lead, Training, Model Risk |  |  | Not Started | 0% | Competency framework (FS-specific), training plan, Board AI literacy program, records | APRA CPS 520
7 | 7.2 | Competence | 2 | Require understanding of relevant regulations for all AI staff | HR, AI Governance Lead, Training, Model Risk |  |  | Not Started | 0% | Competency framework (FS-specific), training plan, Board AI literacy program, records | APRA CPS 520
7 | 7.2 | Competence | 3 | Establish ongoing training: responsible AI, bias testing, explainability, financial regulation | HR, AI Governance Lead, Training, Model Risk |  |  | Not Started | 0% | Competency framework (FS-specific), training plan, Board AI literacy program, records | APRA CPS 520
7 | 7.2 | Competence | 4 | Ensure Board and senior management receive AI literacy training for effective oversight | HR, AI Governance Lead, Training, Model Risk |  |  | Not Started | 0% | Competency framework (FS-specific), training plan, Board AI literacy program, records | APRA CPS 520
7 | 7.2 | Competence | 5 | Retain evidence: qualifications, certifications (FRM, PRM, AI-specific), training records | HR, AI Governance Lead, Training, Model Risk |  |  | Not Started | 0% | Competency framework (FS-specific), training plan, Board AI literacy program, records | APRA CPS 520
7 | 7.3 | Awareness | 1 | Ensure all staff aware of AI policy and responsibilities | AI Governance Lead, HR, Communications, Compliance |  |  | Not Started | 0% | Awareness materials, attendance records, scenario exercise records, staff surveys
7 | 7.3 | Awareness | 2 | Targeted awareness: front-office (explaining AI to customers), operations (monitoring), compliance (regulatory) | AI Governance Lead, HR, Communications, Compliance |  |  | Not Started | 0% | Awareness materials, attendance records, scenario exercise records, staff surveys
7 | 7.3 | Awareness | 3 | Raise awareness of generative AI risks: data leakage, hallucination, IP, client confidentiality | AI Governance Lead, HR, Communications, Compliance |  |  | Not Started | 0% | Awareness materials, attendance records, scenario exercise records, staff surveys
7 | 7.3 | Awareness | 4 | Scenario-based training: biased lending decision, fraud model excessive false positives | AI Governance Lead, HR, Communications, Compliance |  |  | Not Started | 0% | Awareness materials, attendance records, scenario exercise records, staff surveys
7 | 7.3 | Awareness | 5 | Ensure understanding of whistleblowing and escalation channels for AI concerns | AI Governance Lead, HR, Communications, Compliance |  |  | Not Started | 0% | Awareness materials, attendance records, scenario exercise records, staff surveys
7 | 7.4 | Communication | 1 | Define communication plan: internal (Board, committees, business lines) and external (regulators, customers) | AI Governance Lead, Regulatory Affairs, Customer Experience |  |  | Not Started | 0% | Communication plan, regulatory engagement log, customer disclosure templates, incident protocol | Consumer protection
7 | 7.4 | Communication | 2 | Establish regulatory communication protocols: proactive engagement, inquiry response, breach notification | AI Governance Lead, Regulatory Affairs, Customer Experience |  |  | Not Started | 0% | Communication plan, regulatory engagement log, customer disclosure templates, incident protocol | Consumer protection
7 | 7.4 | Communication | 3 | Define customer communication standards: right to explanation, complaints handling for AI outcomes | AI Governance Lead, Regulatory Affairs, Customer Experience |  |  | Not Started | 0% | Communication plan, regulatory engagement log, customer disclosure templates, incident protocol | Consumer protection
7 | 7.4 | Communication | 4 | Establish AI incident communication protocol with triggers, escalation, and disclosure requirements | AI Governance Lead, Regulatory Affairs, Customer Experience |  |  | Not Started | 0% | Communication plan, regulatory engagement log, customer disclosure templates, incident protocol | Consumer protection
7 | 7.5 | Documented Information | 1 | Establish document control aligned with regulatory retention requirements | AI Governance Lead, Document Control, Model Risk, Technology |  |  | Not Started | 0% | Document control procedure, model documentation standards, model inventory, retention schedule | SR 11-7, APRA
7 | 7.5 | Documented Information | 2 | Define model documentation standards: model cards, technical specs, validation reports, approvals | AI Governance Lead, Document Control, Model Risk, Technology |  |  | Not Started | 0% | Document control procedure, model documentation standards, model inventory, retention schedule | SR 11-7, APRA
7 | 7.5 | Documented Information | 3 | Ensure version control for models, datasets, AI configs (MLOps) | AI Governance Lead, Document Control, Model Risk, Technology |  |  | Not Started | 0% | Document control procedure, model documentation standards, model inventory, retention schedule | SR 11-7, APRA
7 | 7.5 | Documented Information | 4 | Maintain comprehensive model inventory with lifecycle status, risk tier, validation status | AI Governance Lead, Document Control, Model Risk, Technology |  |  | Not Started | 0% | Document control procedure, model documentation standards, model inventory, retention schedule | SR 11-7, APRA
7 | 7.5 | Documented Information | 5 | Ensure audit trail and retention per regulatory requirements (7+ years) | AI Governance Lead, Document Control, Model Risk, Technology |  |  | Not Started | 0% | Document control procedure, model documentation standards, model inventory, retention schedule | SR 11-7, APRA
8 | 8.1 | Operational Planning and Control | 1 | Implement model lifecycle: development, peer review, validation gate, deployment approval, monitoring, retirement | AI Governance Lead, CTO, Model Risk, IT Ops, Procurement |  |  | Not Started | 0% | Model lifecycle procedure, acceptance criteria, MLOps docs, third-party records, GenAI controls | SR 11-7, CPS 230, DORA
8 | 8.1 | Operational Planning and Control | 2 | Define acceptance criteria: performance thresholds, fairness benchmarks, explainability, stability tests | AI Governance Lead, CTO, Model Risk, IT Ops, Procurement |  |  | Not Started | 0% | Model lifecycle procedure, acceptance criteria, MLOps docs, third-party records, GenAI controls | SR 11-7, CPS 230, DORA
8 | 8.1 | Operational Planning and Control | 3 | Implement MLOps: reproducible pipelines, data lineage, model versioning, automated testing, rollback | AI Governance Lead, CTO, Model Risk, IT Ops, Procurement |  |  | Not Started | 0% | Model lifecycle procedure, acceptance criteria, MLOps docs, third-party records, GenAI controls | SR 11-7, CPS 230, DORA
8 | 8.1 | Operational Planning and Control | 4 | Manage third-party AI: due diligence, ongoing monitoring, contractual obligations, concentration risk | AI Governance Lead, CTO, Model Risk, IT Ops, Procurement |  |  | Not Started | 0% | Model lifecycle procedure, acceptance criteria, MLOps docs, third-party records, GenAI controls | SR 11-7, CPS 230, DORA
8 | 8.1 | Operational Planning and Control | 5 | Implement GenAI controls: input/output filtering, grounding, citation, human-in-the-loop | AI Governance Lead, CTO, Model Risk, IT Ops, Procurement |  |  | Not Started | 0% | Model lifecycle procedure, acceptance criteria, MLOps docs, third-party records, GenAI controls | SR 11-7, CPS 230, DORA
8 | 8.1 | Operational Planning and Control | 6 | Ensure AI changes follow model change and IT change management processes | AI Governance Lead, CTO, Model Risk, IT Ops, Procurement |  |  | Not Started | 0% | Model lifecycle procedure, acceptance criteria, MLOps docs, third-party records, GenAI controls | SR 11-7, CPS 230, DORA
8 | 8.2 | AI Risk Assessment (Operational) | 1 | Perform ongoing assessments: at deployment, periodically (min. annually), on material change | Model Risk, AI Governance Lead, Data Science, Operational Risk |  |  | Not Started | 0% | Ongoing risk reports, monitoring dashboards, drift detection, backtesting results, OpRisk reports | CPS 220, Basel
8 | 8.2 | AI Risk Assessment (Operational) | 2 | Monitor for model drift, concept drift, data drift across all deployed AI | Model Risk, AI Governance Lead, Data Science, Operational Risk |  |  | Not Started | 0% | Ongoing risk reports, monitoring dashboards, drift detection, backtesting results, OpRisk reports | CPS 220, Basel
8 | 8.2 | AI Risk Assessment (Operational) | 3 | Assess emerging risks: adversarial attacks, data poisoning, prompt injection for LLMs | Model Risk, AI Governance Lead, Data Science, Operational Risk |  |  | Not Started | 0% | Ongoing risk reports, monitoring dashboards, drift detection, backtesting results, OpRisk reports | CPS 220, Basel
8 | 8.2 | AI Risk Assessment (Operational) | 4 | Evaluate backtesting and benchmarking against acceptance thresholds | Model Risk, AI Governance Lead, Data Science, Operational Risk |  |  | Not Started | 0% | Ongoing risk reports, monitoring dashboards, drift detection, backtesting results, OpRisk reports | CPS 220, Basel
8 | 8.2 | AI Risk Assessment (Operational) | 5 | Integrate results into enterprise operational risk reporting (APRA CPS 220 / Basel) | Model Risk, AI Governance Lead, Data Science, Operational Risk |  |  | Not Started | 0% | Ongoing risk reports, monitoring dashboards, drift detection, backtesting results, OpRisk reports | CPS 220, Basel
8 | 8.3 | AI Risk Treatment | 1 | Implement treatment plans: enhancements, additional controls, human oversight, restrictions, retirement | Model Risk, AI Governance Lead, Risk Owners, CRO |  |  | Not Started | 0% | SoA (FS-contextualized), treatment plans, validation reports, risk acceptance, circuit breaker docs | SR 11-7
8 | 8.3 | AI Risk Treatment | 2 | Produce SoA mapping Annex A/B controls to financial-services context | Model Risk, AI Governance Lead, Risk Owners, CRO |  |  | Not Started | 0% | SoA (FS-contextualized), treatment plans, validation reports, risk acceptance, circuit breaker docs | SR 11-7
8 | 8.3 | AI Risk Treatment | 3 | Apply controls proportionate to risk tier (high-risk credit/trading vs. low-risk analytics) | Model Risk, AI Governance Lead, Risk Owners, CRO |  |  | Not Started | 0% | SoA (FS-contextualized), treatment plans, validation reports, risk acceptance, circuit breaker docs | SR 11-7
8 | 8.3 | AI Risk Treatment | 4 | Implement: pre-deployment validation, ongoing monitoring, champion-challenger, circuit breakers | Model Risk, AI Governance Lead, Risk Owners, CRO |  |  | Not Started | 0% | SoA (FS-contextualized), treatment plans, validation reports, risk acceptance, circuit breaker docs | SR 11-7
8 | 8.3 | AI Risk Treatment | 5 | Obtain risk owner sign-off on residual risk with documented rationale | Model Risk, AI Governance Lead, Risk Owners, CRO |  |  | Not Started | 0% | SoA (FS-contextualized), treatment plans, validation reports, risk acceptance, circuit breaker docs | SR 11-7
8 | 8.4 | AI System Impact Assessment (Operational) | 1 | Conduct ongoing impact monitoring: disparate impact on lending/insurance, customer outcome testing | AI Governance Lead, Compliance, Customer Experience, Model Risk |  |  | Not Started | 0% | Impact monitoring reports, customer outcome analysis, stakeholder engagement, remediation docs | Fair lending, Consumer duty
8 | 8.4 | AI System Impact Assessment (Operational) | 2 | Monitor for adverse outcomes: increased complaints, disproportionate denials, pricing anomalies | AI Governance Lead, Compliance, Customer Experience, Model Risk |  |  | Not Started | 0% | Impact monitoring reports, customer outcome analysis, stakeholder engagement, remediation docs | Fair lending, Consumer duty
8 | 8.4 | AI System Impact Assessment (Operational) | 3 | Engage consumer advocacy groups, financial counsellors, customer panels | AI Governance Lead, Compliance, Customer Experience, Model Risk |  |  | Not Started | 0% | Impact monitoring reports, customer outcome analysis, stakeholder engagement, remediation docs | Fair lending, Consumer duty
8 | 8.4 | AI System Impact Assessment (Operational) | 4 | Compare actual impacts against pre-deployment predictions | AI Governance Lead, Compliance, Customer Experience, Model Risk |  |  | Not Started | 0% | Impact monitoring reports, customer outcome analysis, stakeholder engagement, remediation docs | Fair lending, Consumer duty
8 | 8.4 | AI System Impact Assessment (Operational) | 5 | Trigger remediation: model recalibration, override procedures, customer remediation programs | AI Governance Lead, Compliance, Customer Experience, Model Risk |  |  | Not Started | 0% | Impact monitoring reports, customer outcome analysis, stakeholder engagement, remediation docs | Fair lending, Consumer duty
9 | 9.1 | Monitoring, Measurement, Analysis, and Evaluation | 1 | Define KPIs: accuracy (AUC, Gini), fairness (SPD, DI ratio, equalised odds), FP/FN rates, explainability coverage | Model Risk, AI Governance Lead, Data Science, Compliance |  |  | Not Started | 0% | KPI/KRI dashboards, model monitoring reports, compliance metrics, AIMS self-assessment | SR 11-7
9 | 9.1 | Monitoring, Measurement, Analysis, and Evaluation | 2 | Monitor compliance KPIs: % models validated on time, open findings, regulatory remediation, breach incidents | Model Risk, AI Governance Lead, Data Science, Compliance |  |  | Not Started | 0% | KPI/KRI dashboards, model monitoring reports, compliance metrics, AIMS self-assessment | SR 11-7
9 | 9.1 | Monitoring, Measurement, Analysis, and Evaluation | 3 | Implement real-time monitoring for high-risk AI: fraud, trading, credit stability | Model Risk, AI Governance Lead, Data Science, Compliance |  |  | Not Started | 0% | KPI/KRI dashboards, model monitoring reports, compliance metrics, AIMS self-assessment | SR 11-7
9 | 9.1 | Monitoring, Measurement, Analysis, and Evaluation | 4 | Establish model performance dashboards for 1L, 2L, 3L functions | Model Risk, AI Governance Lead, Data Science, Compliance |  |  | Not Started | 0% | KPI/KRI dashboards, model monitoring reports, compliance metrics, AIMS self-assessment | SR 11-7
9 | 9.1 | Monitoring, Measurement, Analysis, and Evaluation | 5 | Evaluate AIMS effectiveness through periodic self-assessment | Model Risk, AI Governance Lead, Data Science, Compliance |  |  | Not Started | 0% | KPI/KRI dashboards, model monitoring reports, compliance metrics, AIMS self-assessment | SR 11-7
9 | 9.2 | Internal Audit | 1 | Integrate AI audit into annual audit plan with risk-based frequency | Internal Audit, AI Governance Lead, Board Audit Committee |  |  | Not Started | 0% | Audit plan, AI audit reports, auditor competence, Board papers, corrective action tracking | APRA, SR 11-7
9 | 9.2 | Internal Audit | 2 | Scope: AI governance framework, model lifecycle, data governance, third-party AI, customer outcomes | Internal Audit, AI Governance Lead, Board Audit Committee |  |  | Not Started | 0% | Audit plan, AI audit reports, auditor competence, Board papers, corrective action tracking | APRA, SR 11-7
9 | 9.2 | Internal Audit | 3 | Ensure auditors have AI/ML competence or engage specialist resources | Internal Audit, AI Governance Lead, Board Audit Committee |  |  | Not Started | 0% | Audit plan, AI audit reports, auditor competence, Board papers, corrective action tracking | APRA, SR 11-7
9 | 9.2 | Internal Audit | 4 | Audit regulatory alignment: SR 11-7, APRA CPG 235, EU AI Act | Internal Audit, AI Governance Lead, Board Audit Committee |  |  | Not Started | 0% | Audit plan, AI audit reports, auditor competence, Board papers, corrective action tracking | APRA, SR 11-7
9 | 9.2 | Internal Audit | 5 | Report findings to Board Audit Committee with risk ratings and remediation timelines | Internal Audit, AI Governance Lead, Board Audit Committee |  |  | Not Started | 0% | Audit plan, AI audit reports, auditor competence, Board papers, corrective action tracking | APRA, SR 11-7
9 | 9.2 | Internal Audit | 6 | Track corrective actions to closure with independent verification | Internal Audit, AI Governance Lead, Board Audit Committee |  |  | Not Started | 0% | Audit plan, AI audit reports, auditor competence, Board papers, corrective action tracking | APRA, SR 11-7
9 | 9.3 | Management Review | 1 | Conduct reviews at least semi-annually (financial regulators expect frequent oversight) | CRO, CEO, Board Risk Committee, AI Governance Lead |  |  | Not Started | 0% | Review minutes, Board Risk Committee papers, action tracker, regulatory impact assessments | CPS 220
9 | 9.3 | Management Review | 2 | Review: model inventory, validation pipeline, risk metrics, audit findings, incidents, regulatory developments, complaints | CRO, CEO, Board Risk Committee, AI Governance Lead |  |  | Not Started | 0% | Review minutes, Board Risk Committee papers, action tracker, regulatory impact assessments | CPS 220
9 | 9.3 | Management Review | 3 | Assess AI governance resources and capability against AI adoption growth | CRO, CEO, Board Risk Committee, AI Governance Lead |  |  | Not Started | 0% | Review minutes, Board Risk Committee papers, action tracker, regulatory impact assessments | CPS 220
9 | 9.3 | Management Review | 4 | Review emerging regulatory requirements and assess AIMS impact | CRO, CEO, Board Risk Committee, AI Governance Lead |  |  | Not Started | 0% | Review minutes, Board Risk Committee papers, action tracker, regulatory impact assessments | CPS 220
9 | 9.3 | Management Review | 5 | Document decisions, actions, resource commitments with accountability and deadlines | CRO, CEO, Board Risk Committee, AI Governance Lead |  |  | Not Started | 0% | Review minutes, Board Risk Committee papers, action tracker, regulatory impact assessments | CPS 220
10 | 10.1 | Continual Improvement | 1 | Use audit, monitoring, regulatory feedback for improvement opportunities | AI Governance Lead, CRO, Regulatory Affairs |  |  | Not Started | 0% | Improvement register, benchmarking reports, lessons learned log, industry engagement records
10 | 10.1 | Continual Improvement | 2 | Benchmark AI governance maturity against industry peers and regulatory expectations | AI Governance Lead, CRO, Regulatory Affairs |  |  | Not Started | 0% | Improvement register, benchmarking reports, lessons learned log, industry engagement records
10 | 10.1 | Continual Improvement | 3 | Integrate lessons from AI incidents, near-misses, and industry enforcement actions | AI Governance Lead, CRO, Regulatory Affairs |  |  | Not Started | 0% | Improvement register, benchmarking reports, lessons learned log, industry engagement records
10 | 10.1 | Continual Improvement | 4 | Track improvement initiatives with ownership and timelines | AI Governance Lead, CRO, Regulatory Affairs |  |  | Not Started | 0% | Improvement register, benchmarking reports, lessons learned log, industry engagement records
10 | 10.1 | Continual Improvement | 5 | Participate in industry working groups and regulatory consultations on AI governance | AI Governance Lead, CRO, Regulatory Affairs |  |  | Not Started | 0% | Improvement register, benchmarking reports, lessons learned log, industry engagement records
10 | 10.2 | Nonconformity and Corrective Action | 1 | Establish NC process integrated with incident management and regulatory breach reporting | AI Governance Lead, Operational Risk, Compliance, CRO |  |  | Not Started | 0% | NC log, RCA records, CA records with SLAs, Board/regulatory notification records | CPS 220, Breach reporting
10 | 10.2 | Nonconformity and Corrective Action | 2 | Define AI-specific NCs: model failures, biased outcomes, validation gaps, data breaches, unauthorised AI use | AI Governance Lead, Operational Risk, Compliance, CRO |  |  | Not Started | 0% | NC log, RCA records, CA records with SLAs, Board/regulatory notification records | CPS 220, Breach reporting
10 | 10.2 | Nonconformity and Corrective Action | 3 | Conduct root cause analysis (5 Whys, fishbone) for material NCs | AI Governance Lead, Operational Risk, Compliance, CRO |  |  | Not Started | 0% | NC log, RCA records, CA records with SLAs, Board/regulatory notification records | CPS 220, Breach reporting
10 | 10.2 | Nonconformity and Corrective Action | 4 | Implement CAs with SLAs: critical 30 days, high 60 days, medium 90 days | AI Governance Lead, Operational Risk, Compliance, CRO |  |  | Not Started | 0% | NC log, RCA records, CA records with SLAs, Board/regulatory notification records | CPS 220, Breach reporting
10 | 10.2 | Nonconformity and Corrective Action | 5 | Report material AI NCs to Board and regulators as required | AI Governance Lead, Operational Risk, Compliance, CRO |  |  | Not Started | 0% | NC log, RCA records, CA records with SLAs, Board/regulatory notification records | CPS 220, Breach reporting

## Dashboard
ISO 42001 Implementation Dashboard — Financial Services
Overall Progress Summary
Metric | Value
Total Tasks | 132
Not Started | 132
In Progress | 0
Under Review | 0
Complete | 0
N/A | 0
Completion Rate (%) | 0
Progress by Clause
Clause | Title | Total Tasks | Complete | % Complete
4 | Context of the Organization | 22 | 0 | 0
5 | Leadership | 18 | 0 | 0
6 | Planning | 22 | 0 | 0
7 | Support | 23 | 0 | 0
8 | Operation | 21 | 0 | 0
9 | Performance Evaluation | 16 | 0 | 0
10 | Improvement | 10 | 0 | 0

## Regulatory Alignment
Regulation / Standard | Jurisdiction | Key AI Requirements | Relevant ISO 42001 Clauses | Compliance Status
APRA CPS 230 (Operational Risk) | Australia | Operational resilience incl. AI; third-party risk; critical operations | 4.3, 8.1 | Not Assessed
APRA CPS 234 (Information Security) | Australia | Information security for AI systems; data protection; testing | 4.2, 7.5, 8.1 | Not Assessed
APRA CPG 235 (Data Risk) | Australia | Data governance, quality, lineage for AI/analytics | 7.5, 8.1, 8.2 | Not Assessed
APRA CPS 220 (Risk Management) | Australia | Operational risk framework incl. AI; risk appetite; Board oversight | 5.1, 6.1, 9.3 | Not Assessed
EU AI Act | EU | Risk-based AI classification; high-risk requirements for credit/insurance | 4.3, 6.1.4, 8.3 | Not Assessed
DORA | EU | ICT risk management incl. AI; third-party concentration; incident reporting | 8.1, 10.2 | Not Assessed
SR 11-7 (Model Risk Management) | USA (Fed/OCC) | Model validation, governance, monitoring; independent validation | 5.2, 5.3, 8.1, 9.2 | Not Assessed
FCA / PRA AI Guidance | UK | Consumer duty; fairness; explainability; accountability | 5.2, 6.1.4, 8.4 | Not Assessed
MiFID II / MiFIR | EU | Algorithmic trading controls; market conduct; best execution | 8.1, 8.3 | Not Assessed
Basel III/IV (BCBS 239) | Global | OpRisk capital; model risk; data aggregation | 6.1, 8.2, 9.1 | Not Assessed
OECD AI Principles | Global | Transparency, accountability, robustness, fairness | 5.2, 6.1 | Not Assessed
Australian Privacy Act / APPs | Australia | Automated decision-making rights; PIAs; consent | 6.1.4, 7.4 | Not Assessed
GDPR (where applicable) | EU | Right to explanation (Art. 22); DPIAs; data minimisation | 6.1.4, 7.4, 7.5 | Not Assessed

## Document Register
# | Document Name | Clause Ref | Regulatory Alignment | Owner | Version | Date Created | Last Reviewed | Status | Location/Link
1 | AIMS Scope Statement | 4.3 | APRA CPS 230 |  |  |  |  | Draft
2 | Organizational Context Report | 4.1 | [5 empty] | Draft
3 | Interested Parties & Regulatory Register | 4.2 | Multiple |  |  |  |  | Draft
4 | AIMS Process Map (Three Lines of Defence) | 4.4 | SR 11-7, APRA |  |  |  |  | Draft
5 | AI Policy (Board-approved) | 5.2 | SR 11-7, APRA, FCA |  |  |  |  | Draft
6 | Generative AI Acceptable Use Policy | 5.2 | [5 empty] | Draft
7 | RACI Matrix / Governance Org Chart | 5.3 | SR 11-7 |  |  |  |  | Draft
8 | AI Risk Assessment Methodology | 6.1 | CPS 220, Basel |  |  |  |  | Draft
9 | AI Risk Register (integrated) | 6.1/8.2 | CPS 220 |  |  |  |  | Draft
10 | AI Impact Assessment Methodology | 6.1.4 | EU AI Act, APPs |  |  |  |  | Draft
11 | Disparate Impact Analysis Reports | 6.1.4 | Fair lending |  |  |  |  | Draft
12 | AI Objectives & KRIs/KPIs | 6.2 | [5 empty] | Draft
13 | Statement of Applicability (SoA) | 8.3 | [5 empty] | Draft
14 | Risk Treatment Plan | 8.3 | [5 empty] | Draft
15 | Model Lifecycle Procedure | 8.1 | SR 11-7 |  |  |  |  | Draft
16 | Model Documentation Standards | 7.5 | SR 11-7, APRA |  |  |  |  | Draft
17 | Model Inventory | 7.5/8.1 | SR 11-7 |  |  |  |  | Draft
18 | Third-Party AI Due Diligence Records | 8.1 | CPS 230, DORA |  |  |  |  | Draft
19 | Competency Framework (FS-specific) | 7.2 | [5 empty] | Draft
20 | Training Records (incl. Board AI literacy) | 7.2 | APRA CPS 520 |  |  |  |  | Draft
21 | Communication Plan | 7.4 | [5 empty] | Draft
22 | Customer Disclosure Templates | 7.4/8.4 | Consumer protection |  |  |  |  | Draft
23 | Monitoring Plan & KPI Dashboard | 9.1 | [5 empty] | Draft
24 | Model Validation Reports | 8.1/9.1 | SR 11-7 |  |  |  |  | Draft
25 | Internal AI Audit Reports | 9.2 | [5 empty] | Draft
26 | Management Review / Board Papers | 9.3 | CPS 220 |  |  |  |  | Draft
27 | NC & Corrective Action Log | 10.2 | Breach reporting |  |  |  |  | Draft
28 | Continual Improvement Register | 10.1 | [5 empty] | Draft

## Timeline
Month | Phase | Focus Area | Key Milestones | Status
1 | Phase 1: Initiation | Board Endorsement & Setup | Board resolution, project team, budget, regulatory advisor engaged | Not Started
2 | Phase 1: Initiation | Regulatory Mapping | Regulatory requirements mapped to ISO 42001, gap analysis initiated | Not Started
3 | Phase 1: Initiation | Gap Analysis & Scope | Gap analysis complete, scope defined, AI/model inventory, risk classification | Not Started
4 | Phase 2: Design | AI Policy & Risk Framework | AI Policy board-approved, risk methodology aligned to MRM, risk appetite set | Not Started
5 | Phase 2: Design | Risk & Impact Assessments | Risk assessments complete, disparate impact analyses, impact assessments | Not Started
6 | Phase 2: Design | Controls & SoA | Controls selected per risk tier, SoA drafted, validation procedures designed | Not Started
7 | Phase 2: Design | Procedures & Documentation | Procedures finalized, model documentation standards, training materials ready | Not Started
8-9 | Phase 3: Implementation | Rollout | Processes operational, Three Lines trained, model inventory populated | Not Started
10-11 | Phase 3: Implementation | Monitoring & Evidence | Dashboards live, validation pipeline, 3+ months evidence | Not Started
12 | Phase 3: Implementation | Operational Maturity | Full evidence, customer outcome testing, model benchmarks | Not Started
13 | Phase 4: Assurance | Internal Audit | Full AI audit, findings documented, corrective actions initiated | Not Started
14 | Phase 4: Assurance | Management & Board Review | Management review, Board Risk Committee review, improvements defined | Not Started
15 | Phase 4: Assurance | Pre-certification | CAs closed, docs complete, readiness assessment, regulatory engagement | Not Started
16-18 | Phase 4: Assurance | Certification Audit | Stage 1 (documentation) and Stage 2 (on-site), surveillance planning | Not Started

## AI Use Cases
AI Use Case | Business Line | Risk Tier | Key Concerns | In Scope? | System Owner | Validation Status | Last Validated
Credit scoring / lending decisions | Retail/Corporate Banking | High | Bias, fair lending, explainability, disparate impact | Yes
Fraud detection | Operations/Risk | High | False positives, model drift, adversarial attacks, real-time performance | Yes
AML / KYC / sanctions screening | Compliance | High | False negatives, alert fatigue, regulatory expectations, data quality | Yes
Algorithmic / HF trading | Markets/Trading | High | Market integrity, circuit breakers, flash crash, conduct risk, MiFID II | Yes
Insurance pricing / underwriting | Insurance | High | Discrimination, proxy variables, transparency, customer outcomes | Yes
Robo-advisory / wealth management | Wealth | High | Suitability, best interest duty, personalisation risks | Yes
Customer service chatbots / LLMs | Customer Experience | Medium | Hallucination, data leakage, complaints, misinformation, conduct | Yes
Customer onboarding / identity verification | Operations | Medium | Biometric bias, privacy, false rejection, accessibility | Yes
Collections / debt management | Operations | Medium | Vulnerable customer identification, conduct risk, fair treatment | Yes
Internal analytics / BI / reporting | Various | Low | Data quality, decision reliance, governance proportionality | Yes
Process automation (RPA + AI) | Operations | Low | Error propagation, monitoring, change management | Yes